## Plans
1		Feature Name	Status	Priority	dependency	Version	B_WEB	F_WEB	Android	Start	End	Developer/Description	User Journey	Description	implementation	Comments	User Journey
2	1	User Account	N	H		99.1	Y							User can able to register with mobile number or email address. This mobile number and email address will be used for password recovery. / Need to verify email address and mobile number. / Here option can be given that how u wanna to use the site as dooner or needy one.	An UI will be built. Where people will enter their user email address or mobile number. Now here is a big quesiton : JWT or Basic Atithentication. As MVC I think basic can be used. Here is the question come of mobile number validation
3		1. Register					Y
4		2. Login					Y
5		3. Forgot password.
6		4. Change password
7		5. Log out
8	2	Validation	N	H		99.1	Y					Have to verify the email address or mobile number that been used to register an account. Have to verify because later if password forgotten the to recvoer password these email, phone number will be used.		It may possible that people can do account by fake ID or mobile number. For mobile number we can use sms verification system	Need to buy sms from sms server. Have to set up a mail server to send mail and validate the account.
9		1. Email Verification					Y	Y
10		1. Sending Code					Y	Y				A code will be sent to the email address the code will be valid for 180 seconds			have to maintain a code table
11		2. verifying the token.					Y
12		2. SMS verification					n	n
13		1. Have to buy SMS from server					n	n
14		2. Sending code					n	n
15		3. Verifying the account.					n	n
16	3	User Profile Managing	N	H		99.1	Y	Y						Every user either donner or agent must have to be registeredd first and have to make a profile first. Some master account may be set. By hand. / Basic CRUD operation on it. / User profile can be divided in to essential and optional Two Parts. / For essential name, address, age etc. In case of optional user other information like blood pressure, weigh etc. / Must have to keep a mobile number and also an alternative number. Have to regularly round up that number that the number is active. Need to verify the number. / 1. Personal Information / 2. Physical information that needed to confirm that dooner is eligible for blood donation. / User’s all information may not be seen by all. Each information must have a privacy level. Some information will be must be seen by the agent.
17		1. Profile Management				99.1	Y	Y
18		1. Phone Number Management		H	0		Y	Y				Within the edit delete will, means if any filed not have data it will be empty.
19		1. Edit		H	0		Y	Y				Depricated because thought it was not needed.
20		2. Delete		H	0		n	n
21		3. Add		H	0
22		2. Agent Management				99.1	n							user can search agent can able to change his current user.
23	4	User Blood Donation History	N	H	0	99.1	Y					a note can be kept about the donation of the blood.		User can keep their blood donation history. It is very important cause when blood donner search will be done then this information will be needed. / Here CRUD operation can be done. / User can update their history from android app. From android app easily by one press history can be updated. / Privacy level can be set with the history. Who can see the history. But agent will able to see the history.
24		1. Edit		H	0	99.1	Y	Y				Dooner can edit their history like where they went to give blood in which date they gone.
25		2. Delete		H	0	99.1	Y	Y
26		3. Add		H	0	99.1	Y	Y
27		4. Search		H	0	99.1	Y	Y
28		5. Short		H	0	99.1	Y	Y
29	5	Post	N			99.1	n	n						People can post what kind of blood they need. Have to CRUD operation. Post may contain Place of means, where blood needed, when needed, how much needed. Any special requirment of the dooner. In the place we can use drop down menu to select place so that based on their post auto suggestion can be done. But have to careful selecting from drop menu can be annoying for person in search of blood. We can make it optional.
30		1. My Post			0	99.1	n	n				Here use can see manage his post like what he has given so far and so on.
31		1. Give Post			0	99.1	n	n				Giving a new post for blood. In time giving post some things can be obvious that date, patient description, when needed, how many bags, location. Phone number etc.
32		2. Edit post			0	99.1	n	n				Here an existing post can be edited. Constrain and validation have to keep so that any one can not put date before the current date.
33		3. Delete Post			0	99.1	n	n				Existing post can be deleted.
34		4. My Posts			0	99.1	n	n				So far posts given by a use.
35		1. Short My posts			0	99.1	n	n
36		2. Search inside my post			0	99.1	n	n
37		2. Show Other posts			0	99.1	n	n
38		3. Post Saving			0	99.1	n	n
39		1. Remove			0	99.1	n	n				Remove a saved post.
40		2. Short			0	99.1	n	n				Here Post can be shorted in different axis like Blood group, by need date, which have been expired so far meaning the . Or near to expire
41	6	Notifications	N	H		99.2	n	n						When a post done it will notify the Eligable person if . In person profile section there can be box where auto Notifications will be gone. It will alos notify the people who have android app install.		First thought that notification will not be done now but later thought it is very essential thing. / Because many people use mobile phone now a days.
42		1. Send notification
43	7	Emergency Service	N	H		99.1	Y							Emergency can be set by rule like that blood needed within 24 hour or with much blood needed, or rare blood group.
44	8	User Type Management	N	H		99.1	Y					Means an user can be agent. So before to be an agent, must have to register as an user first.		An user can be an Donner, can be an agent. So after register he have to apply for Agent.
45	9	Status	N	H		99.1	Y					When wen to give blood in NITOR then seen a from where there are some fields that have u done any major operation within last 15 days on word, r u in pregnecy, have taken any aspirin type medicine so on. There are some points only for female. So have to keep in mind that based on the user gender we have to show the status points. Need to collect information about these points means what does means what, why need to be concern about those points. / There can be option kept that agent can change the status any one else can change the status if permission given to ther user. / Here have to keep option send message to the user or the agent of the donner that the donner status need to be changed, the dooner might forgot change the state. Or the system pirmary goal is to design a MIS for the blood donation Related people so it might be needed that need to change the state of the user means.		Status means there are certain criteria donate blood like might have to in good health, pregnency. Some of the information are related to just female and might not wanna discover it by other. So these information will be hidden but they will be used in time of search. Here case may happen that people may forgot change their status in such cased a notification system can be build based on their Status. / The status type can be taken a from that have been collected from natinal orthopodics hospital. “National Blood Transfusion Services (NITOR)” / In that from there is option that is only for female.
46	if	1. Update User status										Most of the status edit is “Edit work”
47		2. Privacy										Some people may wan to see their status seen by people. So people can set their private. On such cased it will be shown that the people is avail able for now.
48		3. Auto Update										Status will be automatically update like when a people will give that they have major operation date, then system automatically count w
49	10	Search	N	H		99.1	n	n				The search can be made a public search. Only register user can see the contact information else have to contact with the Agent. / Public0, means any one can able to see it, even he is not registered user. / For registered user, they can able to see the contact information if it made public1, public1 means only the register user can see it. / Public2, means register users will also not able to see the information, only agents can see it.		The most important part. Have to set a master search plan. People will enter their blood required blood group and
50		1. By Most Recently Posted.	N	H		99.1	n	n
51		2. Show from Oldest.	N	H		99.1	n	n
52		3. How by Blood Group.	N	H		99.1	n	n
53		4. Blood Group + Most Recent.	N	H		99.1	n	n
54		5. Blood Group + Oldest.	N	H		99.1	n	n
55		6. Search By location.	N	H		99.1	n	n				Means where the blood needed, how many donner are there in that particular location.
56		7. Save Post		H			n	n
57		8. View a post					n	n				After viewing the post one can able to be agree that he will give blood.
58		9. Searching Based on Status										Searching based on the status means that when we need find out have to keep consideration of their status as it described in the status section. / When people will do common search for in by location or group have to ensure that the people currently nor eligible to give blood they should not be shown in the search result. / But sometimes case may be that people can search donner to save them in their list, in those case search status will be taken in consitartion and shown with status.
		10. Special Search
		This kind search only allowed by the registered users and like search by mobile number and email address but I think this search can available for all.
59	11	Agent	N	H		99.1	Y					The agent account will be maintained by the super admin. Like when some one wants be an agents from super account the permission of the account will be changed. He/She will get access to the methods with the permission “agent”		When a people will apply for agent then the request will be gone the master account admin. There admin account will be added by hand. Every registered account must under within a agent account. An agent account must me under a admin account.
60		1. Apply for Agent					Y					To Apply for agent : have to go to the url loggin, there have to give the option, apply for the agent, but first have to logging, logging fail will give option for loggin. Before saving any agent request, have to check does it exit or not.
61		2. Approve Agent					Y	y
62		3. Show All gents					Y	y
63		4. Remove Agents					y	y				c. freeze
64		1. Bulk Removing					n	n				In one tome more than one donner can be removed
65		5.Frezee An agents					y	y				2. Accepted
66		6. Activating An Agent					y	y				c. active
67		7. Add an agents					y	y				c. accept		Directly an agent can be added. By user name one can search or when user name will be put, then user will be shown. And that user can be added as agent.
68		8. Abdicate Agentship					y	y				4. Freezed
69		9. Transfer use to another agent					N	N				It is possible to transfer a donner form one agent account to another accunt. The user will be notified that u have been transferred to another agent. There option can be kept that donner may reject the transfer.
70		1. Bulk Transfer					N	N
		10. Review Request					y	y				All requested profile with some basic information will be show.
		1. Search					y	y
		2. Accepted					y	y				Mange the requests, so far accepted, request can be freeze from here.
		a. search					y	y
		b. pagination					y	y
		c. freeze					y	y
		3. Rejected					y	y				Mange the requests, so far rejected, request can be accepted/activated from here again.
		a. search					y	y
		b. pagination					y	y
		c. accept					y	y
		4. Freezed					y	y				means an user not want to be an agent any more.
		a. search					y	y
		b. pagination					y	y
		c. active					y	y
		5. Review					y	y
		a. search					y	y
		b. pagination					y	y
		c. accept					y	y
		d. reject					y	y
		3. Batch Approve

71	12	Agent’s Dashboard	N	H		99.1	n	n				Agents personal account.		Here Agents will able to manage the accounts under them. They can delete, add an account from their list. They can also able to change the status that account like eligible to donation or not. They can also able to report an account to the admin. Agents will regularly round up the account and update the account status. / Agents can able transfer one account to another Agents. Agent can relise someone from him, then a notification will be gone to the user account, when a Agent relise some one from him/her then the account will automatically go to admin agents and then admin agents will decide under which new agent his account will be assinged. But I think this feature may be needed rarely cause it is a serious matter agents change may not happen frequently.
		Donner Management
		Review Requests
		Accepted
		Rejected
		Blood request Management
		Review Requests
		Accepted
		Rejected
72	13	Connection	N	L		99.2	n	n						People can make connection with other. First have to send connection request. If receiver accept the request then these people will in connection.		Not need at this moment. Consider the project as a MIS for the people who are involved in blood donation.
73	14	Message	N	L		99.2	n	n						People can send message to each other. And receive each other.		Check reason 14
74	15	Blocking	N	L		99.2	n	n						It is possible to block someone who is bothering some one. Blocked person can not send message to the person who blocked. It is possible to unblock later.		Check reason 14
75	16	Article	N	L		99.2	n	n						The article feature is optional. Cause later this project will be moved to GBD. For that reason article will not be done now.		Check reason 14
76	17	Saved People	N	H	0	99.1	n	n						After searching, it will possible to save the people that u think u mat need later. Edit delete and seach can be done here.
77		1. Add		H	0		n	n
78		2. Remove		H	0		n	n
79		1. Bulk Removing		H	0		n	n
80		3. Notes		H	0		n	n				Mean when was the last date the donner have given blood.
81		4. Last given		H	0		n	n						When this user has last given blood, based on that an automatic
82		5. Searching		H	0		n	n
83	18	Account Control	N	H			n	n						Depending on activity an account can be activated or make deactivated. It may happen that some account are violating the rules and regulation of the organization that account can be deactivated
84		1. Active an account	N	H			n	n
85		2. Deactive an account	N	H		a	n	n						When deactivating an option a note can be kept that what is reason for which the account has been banned.
86		3. Banned an account	N	H			n	n						When an account will be banned then it is email address will kept in a black list and any account can be created further form that email address.
87		4. Show All Accounts	N	H			n	n
88		5. Searching among the accounts.	N	H			n	n
89	19	Donner Database					n	n				There are many people who wants to donate blood but not wants to be a member of the site or not have time or knowledge to maintain the site, their name and contact information can be kept here. / These people’s direct contact information can be kept or a number can be given by which they can be reached. / In time of adding the contact number, have to mention whom number is that.		There may be case happen that all the people who wants to donate blood may not have account in this site. Or may be me N number of reasons of not having account here. Cause my might do not know how to use the site and so on. In those cases a central blood database can be maintained that when some one need blood he/she can search here. Or any registered user can add a dooner in the Database. Here case may happen that one dooner can be added more than once. Here option have to keep that who has added the user. Status of the user. It will not be public only register users can access the public database. / There will an owner of the data, other can not delete the data, they can report or give any objection of the data.
90		1. Add					n	n
91		2. Edit					n	n
92		3. delete					n	n
93		4. Show all Added.					n	n
94		5. Search among my Donners					n	n
95		6. Save					n	n						After searching an in the public doneer list it can be possible to save some of the name in my list.
96		7. Abuse control										Case may happen that some one can be added in public to heras them . To make it control have to keep a control number where people can call and told that there number have been added there without their permission and they are willing to keep the number their any more. / Or they can make a report that there number have been added their with their persmission. Then the number will be deleted from the data base and the user has added the number will be back listed and will be informed. After a certain report about the, his/her account will be disabled. / He/She will lose the ability to add any contact number in the database and all of his/her added contact will be deleted from there.
97
98
99
100	20	Privacy										Mean who can see ur information. Some information will be seen by the agent. And some information by the registered user and some by all in public.
		Types of user :
		Registered										Will able to see the information that are not private.
		No-Registered										In time of search only will able to see the agent number that the dooner belongs to.
		Agent										Will only able to information allowed for agent
		Admin										Will able to see all the information.
		So far 3 type level of Data security found. / When a user will request for a data then the user ID will be checked that what type of is this and based on that data will come. / For private data those field will be filed with data that that the data is private. / Some data will be private and even agent no need to see them like various diseases information, some only female data. / User may not want to disclose him/her donation history and so on.
		1. public										Both All register will able to see the information
		2. agent										Only the user agent will able to the data
		3. private										None will able to see the data accept the admin.

101	21	Public Search										it is possible that u can make ur account available for public search. Any one can see ur contact information. For Public search if u r available then only ur data will be come in public search. Like u r willing to donate blood but u not want to public to see ur information, u only communicated by the agent. Then in public search ur agents information will be seen.
102		Search will be same for all registered non registrered.
103
104
105		Other Works And Notes
106
107
108		Collecting Address location Data										I think this work can be left for now. As people problem, and data collection is not all Have to format the ans need to correct the Data, / One thing can be done that can be communicated with farhan via for Data bur I think it is not suitable time to do that.
109		1. Collecting Division Data.				y	y					From LGED web site.
110		2. Collecting District Data.					y					From LGED web site.
111		3. Collecting All Upzila Name.					y					From LGED web site.
112		4. Collecting All Union Data.					y					From LGED web site.
113		5. Collecting Powroshova Data.					y					Collect the powroshova names from wiki pedia.
114		6. Collecting All wards Data.					y					All pworoshova’s are not in wiki pedia.
115
116		1. 0 Means the system has no Dependency means to develop it we not needed to develop another system
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Data Tables
Index	Table name		Type	Relation Type	Privacy			Description
	Basic Info	Basic Info	Type	Relation Type	Privacy	Privacy	Privacy	Description	Notes
		id
		User ID	String					The user ID may be email address of Mobile number. The user ID will be taken automatically the use has no option to give it. The current logged user id will be taken.
		Name	String
		DoB	String/Date					Validation needed that valid date Inputed, Have to ask Mizan That is there age restriction or not.
		Father or Husband Name	String
		Sex (Male/Female/Other)	String
		Mareterial Status	String
		Profession	String
		Blood_Group	String
		Address		One to One User				A separate table can be kept. If separate table kept then it will be easy to maintain the privacy level. Entire privacy can be maintained by one column. / With a one-to-one realtion. / The Below Data collecting, method will not be in use any more. Cause it may more time. Instead let people to write their location name by Hand. I think it will be more efficiant. In the text field label there can be written “Municipality/Upzilla”, “Union or Ward.” In time of search have to ask in which level u wanna search like, Division, District, Municipality/Upzilla, Eunion/Ward based on it any match search can be done. / The admintrative structure of rural is different from the adminstrative structure from the city. Or Powroshova. / Rural area is Division, District, Upzilla, Union. / Urban area may be “Powroshova”, each Powroshova is consisted of several. / Here may be bad data structure can take place like. Because we are not certain and sure about the adminastrative structure of Bangladesh. / So in a single table can be kept where with multiple level of data. Each data will keep the reference of the a address means id of division, dist, Upzilla etc. For urban ares data alos will be kept like that. / Most of the present address will come from urban and most the permanent address may come from rural area. / Have to keep in mind that Powroshova and City corporation are not same thing. / There might some ineffeciant work may be done but nothing have to do. Cause have to take the project production soon. / Have to collect the all the powroshova name.
		Current		one to one address				Have to make all fields Mendatory.
		Division	String
		Dist	String
		Municipality/Upzila	String
		Union/ward	String
		Street	String					Means detailed information like House number etc.
		Permanent		one to one address				Have to make all fields Mendatory.
		Division	String
		Dist	String
		Municipality/Upzilla	String
		Union/ward	String
		creation_date	String
		last_updated	String					A trigger can be used to keep track
		available	String					it means that r u available or willing to donate blood now or not. Some times it may happen that u might not available to donate blood for now N number of reasons.

	Phone Numbers	Phone Numbers		One to Many Profile				Here Multiple phone number can be added.
		index (PK)	int					auto
		User ID	String
		number	String
		date	String

	Emergency Contact Info	Emergency Contact Info		One to Many Profile				One-to-Many / It can be a phone number of someone whom the user trust more. Or here can be address of a any such that the person can be contacted in any emergency.
		User ID	String
		index	int	ID				Auto
		Name	String
		Phone	String
		Mail	String
		Address	String
		relation	String	means relation with that person.

	Physical Info	Physical Info		One to One User Join Column				These data are variable.
		Age (Auto from DoB)	int
		Weight	float
		RBC	float
		Blood Pressure	String
		Pulse	int
		Body Temperature	float

	Blood Donation History	Blood Donation History
		index (PK)	int					Auto
		User ID	String
		date	String/Date					If no date given by default current date have to take.
		Location						Here All fields not need to give inout.
		Country	String
		Division	String
		Dist	String
		Municipality/Upzilla	String
		Union/ward	String
		Hospital Name	String
		Hospital Address	String
		Patient Description	String
		Reference Name	String					Who asked blood to u. Here case may happen donner can get request not belongs ot the MIS will be built.
		Notes	CLOB

	Post	Post	Blood related post. Means blood need post.
		Index (PK)	Auto (PK)
		User ID						Who is posting the post.
		Blood Type
		Location						CLOB kept sometimes detailed information may needed like how reach the location so on. / Here if address given in single line, the possibility of getting perfect match will be less. / OR / Here needy can be forced to provide information like as below. / In the note section details how to reach the location.
		Division	String					For better Search
		Dist	String					For better Search
		Municipality/Upzila	String					For better Search
		Union/ward	String					For better Search
		Hospital Name	String					No need any more, cause in the location section will provide the name of the hospital, some times, blood may required other places than hospitals.
		Hospital Address	String
		Patient Gender	String
		Patient Description	CLOB
		Post date	String					Auto
		Need Date	String
		Quantity	int
		Contact info	CLOB
		Status	String					found or not found, expired, etc
		Remarks	CLOB
		donner_found	int					means how many dooner so far found.
		relation						Relation between the poster and patient.
		notes	CLOB					Only seen by the user who has posted, here may information like who has confirmed to give blood so on
		report
		Comments						one to many with

	Agent Request	agent_request
		id
		user_id
		request_date
		Status

	Request Blood to Agent	request_blood_to_agent
		id (PK)
		user_id_seeker(FK)
		blood_post_id
		request_date
		response_date
		Status						served or not
		note_seeker	CLOB					if seeker wanna sent any note to agent.
		note_agent	CLOB					any note from to seeker.
		note_agent_personal	CLOB					any personal note of the agent about any thing.

	Request Donner to Agent	Donner Public Database						if any donner wants to be added under any agent
		id(PK)
		user_id_donner
		request_date
		accept_date
		remove_date
		Status
		note_donner						if donner add any not for the agent.
		note_agent
		note_agent_personal

	Agent Request	id						to be an agent
		request_date
		accept_date
		reject_date
		freeze_date
		Status
		user_id
		note_applicant
		note_admin
		note_personal

	Required Information	Required Information						Have to set Code for every field. And have to maintain another table with the code and the names. / Diseses can be given single name. The value of the filed will be “y” for yes and “n” no.
		হেপাটাইটিস (জন্ডিস)	String
		ম্যালেরিয়া	String
		মৃগী রোগ	String
		ডায়াবেটিস (বহুমূত্র)	String
		যৌন রোগ	String
		এজমা/শাসকষ্ট	String
		একজিমা(চর্ম রোগ )	String
		উচরক্ত চাপ ( হাইপারটেনশন )	String
		কিডনি রোগ	String
		টিবি (যক্ষা)	String
		পাইলস	String
		ক্যান্সার	String
		পেপটিক আলসার	String
		টাইফয়েড	String
		বাত জ্বর	String
		সিফিলিস	String
		রক্ত আমাশয়	String
		রক্ত জনিত রোগ	String
		আনডুলেন্ট ফিভার	String
		মিজিলস/মাম্পস	String
		বর্তমান কি আপনার ? (শুধু মাত্র মহিলাদের জন্য )
		গর্ভপাত হয়েছে	String					abortion
		সাম্প্রতিক ওজন কমে গেছে	String					recent_weight_loss
		বর্তমানে আপনি কি?
		গর্ভাবস্থায়	String					pragnant
		স্তন্নদানকারী মা	String					breast_feeder
		মাসিকের অবস্থায়	String					period
		আপনার কি?
		৬ মাসের মধ্যে মেজর অপারেশন হয়েছে	String					big_operation_6
		৪ সপ্তাহের মধ্যে দাঁত উঠানো হয়েছে	String					teeth_uthano
		৮ সপ্তাহের মধ্যে ভেকসিন বা টিকা নেয়া হয়েছে	String					vacine_8_week
		আপনি কি?
		রক্ত বা রক্তের উপাদান গ্রহণ করেছেন?	String					taken_elementsOf_blood
		১ সপ্তাহের মধ্যে এসপিরিন জাতীয় ঔষধ সেবন করেছেন	String					aspirin_1_week
		মাদকসাক্ত	String					drug_addict
		কোনো নেশা ঔষধ/মাদকদ্রব্য গ্রহণ করেছেন	String					taken_any_drugs
		বিদেশ ভ্রমণ করেন	String					forigen_trip
		বর্তমান কোনো প্রকার ঔষধ গ্রহণ করছেন	String					any_medicine_now
		নিয়মিত স্বেচ্ছায় রক্ত দানে আগ্রহী	String					wiling_regular_dooner
		এখন সুস্থবোধ করছেন	String					feeling_good
		খাবার গ্রহণ করেছেন	String					taken_meal
		আকুপাংচার বা কান ফুটো করেছেন	String					akupancher_hear_hole

	Donner Public Database	Donner Public Database

	Saved User	Saved User
		Index
		User ID			Who is saving
		User ID			Whom ID is being saved.
		Date

## temp
Agent Personal Account
All doners	All donner under a agent
Add donners
remove donners
Free to add donner	First time users must have to go under any agent. / Donners can be free from, agent, will be appeared in public search with phone number
total donners

Accept
Donners Last donate Date
All requests